## README
Requirements and Data Collection – Microinsurance for Mitumba Traders
Prepared 20 Oct 2026 for task due 23 Oct 2026 (assignee: David Guchu)
How to use this workbook
1. Product_Records: one row per product. Rows are pre-filled ONLY from public news/press sources and are marked UNVERIFIED. Replace with policy-wording facts as documents arrive.
2. Document_Tracker: checklist of documents to obtain and their status.
3. Insurer_Questions: questions to put to Jubilee, Britam Connect and CIC Impact (publishing permission, update frequency, etc.). Record answers in the yellow cells.
4. Trader_Questions: the questions the chatbot must answer, grouped by category, with draft Swahili.
5. Loss_Scenarios: how mitumba trader losses map to product types, with gaps clearly marked.
6. Affordability: converts any premium to weekly / monthly / annual equivalents and checks it against a trader's budget.
7. Work_Plan: 20–23 Oct schedule and the three Notion sub-tasks.
8. Sources: every URL used, and what it supports.
Colour legend
Yellow cell = needs to be filled in / confirmed. Blue text = input value you can change. Black text = formula (do not overwrite).
Important cautions
• Nothing in Product_Records has been confirmed against a policy document or by an insurer. Public news figures (e.g. 'premiums from KES 20') are starting points, not facts for the chatbot.
• Jubilee's Imarisha Jamii details come from 2018 launch coverage and may be out of date. Confirm the current product, underwriter and terms.
• No product found so far is confirmed to cover mitumba stock against fire or theft. Do not tell traders such cover exists until an insurer confirms it in writing.
• Each fact the chatbot uses should carry: source, document date, date retrieved, and a confidence label (Policy wording / Brochure / Insurer confirmed / News – unverified).

## Product_Records
Product records (one row per product)
Pre-filled from public news only. Confidence = News – unverified until a policy document or insurer confirms.
ID | Provider (brand) | Underwriter / entity (confirm) | Product name | Product type | Target customers | Coverage / benefits | Sum insured / benefit amounts | Premium (KES) | Premium basis / frequency | Waiting period | Eligibility (age etc.) | Exclusions | How to buy / pay | Claims process & documents | Provider contact | Source URL | Source document date | Date retrieved | Confidence | Publishable? (Y/N/pending) | Update frequency (per insurer) | Verified by / date | Notes / open questions
P01 | Jubilee | Confirm (Jubilee Insurance / partner) | Imarisha Jamii | Health & life micro bundle | Low-income earners; group, family and chama options | Hospital cash (hospitalised 3+ nights), death and disability cover; mobile access (per 2018 launch coverage) | Not stated in source | From KES 20 (headline figure) | Not stated – confirm (daily/weekly/monthly?) | Not stated | Ages 18–75 (per 2018 coverage) | 2018 coverage says 'no exclusions' – MUST verify against policy wording | Mobile phone; launched with Bluewave Microfinance | Not stated |  | https://www.capitalfm.co.ke/business/2018/06/jubilee-insurance-taps-microinsurance-premiums-low-sh20/ | 2018-06-20 | 2026-10-20 | News – unverified (2018, possibly outdated) |  |  |  | Confirm product still sold, current premium table, benefit amounts and exclusions.
P02 | Britam | Britam Microinsurance / Britam Connect (confirm) | Bima ya Wafanyikazi | Medical cover (informal workers) | Domestic workers and informal-sector workers; buyable by individuals, employers or worker groups | Medical cover via Britam network of 600+ health facilities | Not stated in source | About 336 per month (headline); from about 11 per day | Monthly / daily equivalent (per news headline) | Not stated | Not stated | Not stated | Via Britam Connect with Minet Kenya as distribution partner | Not stated |  | https://www.businessdailyafrica.com/bd/corporate/companies/britam-courts-informal-workers-with-monthly-sh336-medical-cover-5540306 | Not captured – confirm | 2026-10-20 | News – unverified |  |  |  | Check if street/market traders qualify as 'informal sector' and whether group enrolment through a market association is possible.
P03 | Britam | Britam (confirm) | Life Bila Noma (with Telkom) | Personal accident + funeral (bundled with airtime/data) | Small-scale traders (Telkom subscribers) | Accident medical expenses; funeral / last-expense cover on death | Not stated in source | Not stated | Bundled with telecom products – confirm | Not stated | Not stated | Not stated | Telkom mobile bundles | Not stated |  | https://www.businessdailyafrica.com/bd/corporate/companies/telkom-britam-offer-traders-bundles-insurance-cover-3655304 | Not captured (older article) – confirm | 2026-10-20 | News – unverified (older) |  |  |  | Confirm product is still on sale.
P04 | CIC | CIC Impact (CIC Microinsurance subsidiary, launched 30 Jul 2026) | MSME & Commercial Risk (name TBC) | Small-business operational protection | MSMEs / small enterprise owners | 'Essential operational protection for small businesses' – scope not specified | Not stated | Annual premiums start below 3,000 (applies to the portfolio generally) | Annual (portfolio headline) | Not stated | Not stated | Not stated | Via digital channels, SACCOs, traders, employers, mobile platforms | Not stated |  | https://hapakenya.com/2026/07/30/cic-insurance-launches-microinsurance-arm-to-safeguard-kenyas-informal-sector/ | 2026-07-30 | 2026-10-20 | News – unverified |  |  |  | HIGH PRIORITY: ask whether this covers stock, fire and theft for market traders; get product name and wording.
P05 | CIC | CIC Impact | Specialized Personal Accident | Personal accident | Boda boda riders, security guards, blue-collar workers, students | Personal accident cover | Not stated | Below 3,000 annual (portfolio headline) | Annual | Not stated | Not stated | Not stated | As above | Not stated |  | https://hapakenya.com/2026/07/30/cic-insurance-launches-microinsurance-arm-to-safeguard-kenyas-informal-sector/ | 2026-07-30 | 2026-10-20 | News – unverified |  |  |  | Ask whether traders can be covered under this or a similar accident product.
P06 | CIC | CIC Impact | Community & Health Safety Nets (group funeral, group medical, daily hospital cash, micro-pension) | Health / funeral / pension (group) | Groups (SACCOs, chamas, associations) | Group funeral, group medical cover, daily hospital cash, micro-pensions | Not stated | Not stated | Not stated | Not stated | Not stated | Not stated | Group enrolment | Not stated |  | https://hapakenya.com/2026/07/30/cic-insurance-launches-microinsurance-arm-to-safeguard-kenyas-informal-sector/ | 2026-07-30 | 2026-10-20 | News – unverified |  |  |  | Relevant if a mitumba traders' association can enrol as a group.
P07 | Jubilee (pipeline) | Jubilee Group with FSD Africa and 7 insurtechs | SME protection pilots (not yet products) | Pilot – SME protection, low-cost distribution, health & wellness links | SMEs, informal workers, farmers, low-income households | To be defined after an 8-week co-creation programme | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Not applicable | Pilots start November 2026 | Not applicable |  | https://capitalfm.africa/jubilee-fsd-africa-partner-with-seven-insurtechs-to-expand-insurance-access/ | 2026-10-07 | 2026-10-20 | News – unverified |  |  |  | Ask Jubilee whether mitumba traders can join the November pilots.
EXAMPLE | Provider | Underwriter | Product name | e.g. Hospital cash | e.g. Market traders | e.g. KES 1,000 per night in hospital | e.g. KES 1,000/night, max 30 nights | e.g. 100 | e.g. Monthly | e.g. 30 days | e.g. 18–65 | e.g. Pre-existing conditions in first 12 months | e.g. M-Pesa paybill 000000 | e.g. Claim form + discharge summary within 30 days | e.g. 0700 000 000 | e.g. https://… | 2026-01-01 | 2026-10-21 | Policy wording | Y | Reviewed quarterly | D. Guchu 2026-10-22 | Example row – delete when real data is added

## Document_Tracker
Document tracker
Update Status as documents are requested and received.
# | Document | Provider | Where to get it | Status | Date requested | Date received | File name / link | Notes
1 | Product brochure(s) – micro products | Jubilee | jubileeinsurance.com; branch; customer care; Jubilee Health/Retail | Not started
2 | Policy wording / terms & conditions | Jubilee | Ask for the Imarisha Jamii wording and any current micro products | Not started
3 | Premium table and benefit schedule | Jubilee | Insurer or partner (e.g. Bluewave Microfinance) | Not started
4 | Claim form and claims procedure | Jubilee | Insurer | Not started
5 | FAQs / customer guide | Jubilee | Insurer website | Not started
6 | Product brochure(s) – Britam Connect / Britam Microinsurance | Britam | ke.britam.com; Britam Connect channels | Not started
7 | Policy wording – Bima ya Wafanyikazi | Britam | Britam Connect / Minet Kenya | Not started
8 | Premium table and benefit schedule | Britam | Britam Connect | Not started
9 | Claim form and claims procedure | Britam | Britam Connect | Not started
10 | Product brochure(s) – CIC Impact portfolio | CIC | cic.co.ke / cicinsurancegroup.com; CIC branch | Not started
11 | Policy wording – MSME & Commercial Risk | CIC | CIC Impact | Not started
12 | Premium table and benefit schedule | CIC | CIC Impact | Not started
13 | Claim form and claims procedure | CIC | CIC Impact | Not started
14 | List of licensed microinsurers | IRA | ira.go.ke | Not started
15 | Insurance (Microinsurance) Regulations 2020 | IRA / Kenya Law | ira.go.ke; kenyalaw.org | Not started
16 | Insurance Act (relevant provisions) | Kenya Law | kenyalaw.org | Not started
17 | Data Protection Act guidance (consent, retention) | ODPC | odpc.go.ke | Not started
18 | Market loss data: fire, theft, eviction, flooding (Gikomba, Toi, Muthurwa, etc.) | News / county / trader associations | Targeted news search; association leaders | Not started
19 | Financial inclusion / informal-sector insurance research | FSD Kenya, FSD Africa, A2ii, Microinsurance Network | fsdkenya.org; fsdafrica.org; a2ii.org; microinsurancenetwork.org | Not started
| Documents received | 0
| Total documents | 19
| Progress | 0%

## Insurer_Questions
Questions for insurers
Record each insurer's answer in the yellow cells, with date and name of the person who answered.
# | Topic | Question | Jubilee answer | Britam Connect answer | CIC Impact answer
1 | Publishing | May we publish your product details and premiums in a public information chatbot, showing the source and document date?
2 | Publishing | May we quote or summarise brochure and policy wording text? Any wording you require us to use?
3 | Updates | How often do premiums, benefits or terms change? How will you notify us?
4 | Updates | Who is the named contact for updates and corrections?
5 | Product fit | Which of your micro products are open to informal market traders (e.g. mitumba sellers)?
6 | Product fit | Is there any product that covers business stock against fire, theft or damage? If not, is one planned?
7 | Product fit | Can a traders' association, SACCO or chama enrol members as a group? Minimum group size?
8 | Cost | What are the premiums, and can they be paid daily, weekly or monthly (e.g. via M-Pesa)?
9 | Cost | What happens if a trader misses a payment or has a zero-sales week (grace period, lapse, reinstatement)?
10 | Cover | What are the benefit amounts, waiting periods and age limits?
11 | Cover | What are the exclusions? (Please confirm against current policy wording.)
12 | Claims | How do traders claim, which documents are needed, and how long does payout take?
13 | Claims | What is your claims settlement record for micro products (if shareable)?
14 | Distribution | What are the channels to buy: USSD, app, agent, partner, branch? Provider contact numbers?
15 | Compliance | Which licensed entity underwrites each product? Please confirm the IRA approval status.

## Trader_Questions
Questions traders need answered
Swahili is a DRAFT – have a native speaker (ideally a trader) review wording before use.
ID | Category | Question (English) | Swahili (draft) | Answer source needed | Answered? (Y/N) | Notes
Q01 | Basics | What is microinsurance? | Bima ndogo (microinsurance) ni nini? | Regulations / insurer FAQ
Q02 | Basics | Is insurance for someone like me, who sells mitumba? | Je, bima ni ya mtu kama mimi ninayeuza mitumba? | Product eligibility
Q03 | Basics | Is this company licensed and safe? | Je, kampuni hii ina leseni na ni salama? | IRA licensed list
Q04 | Cover | What happens if I get sick and cannot work? | Nikiugua na nisiweze kufanya kazi itakuwaje? | Hospital cash / medical product wording
Q05 | Cover | What happens if I am injured in an accident? | Nikipata ajali itakuwaje? | Personal accident wording
Q06 | Cover | What happens to my family if I die? | Familia yangu itapata nini nikifariki? | Funeral / life wording
Q07 | Cover | Is my stock covered if it burns or is stolen? | Je, mzigo wangu umekingwa ukiungua au kuibiwa? | Business/MSME product wording (confirm exists)
Q08 | Cover | What is not covered? | Nini hakijakingwa? | Exclusions in policy wording
Q09 | Cost | How much does it cost per day, week or month? | Gharama ni kiasi gani kwa siku, wiki au mwezi? | Premium table
Q10 | Cost | Can I pay a small amount daily or weekly through M-Pesa? | Naweza kulipa kiasi kidogo kila siku au wiki kupitia M-Pesa? | Payment terms
Q11 | Cost | What if I miss a payment or have a slow sales week? | Nikikosa kulipa au mauzo yakiwa chini itakuwaje? | Lapse / grace rules
Q12 | Cost | Which cover can I afford with KES [amount] a week? | Ni bima ipi naweza kumudu kwa KES [kiasi] kwa wiki? | Premium table + Affordability sheet
Q13 | Claims | How do I claim and what documents do I need? | Nitadai vipi na nitahitaji hati gani? | Claims procedure
Q14 | Claims | How long until I am paid? | Nitalipwa baada ya muda gani? | Claims procedure
Q15 | Claims | Who do I call if my claim is delayed or refused? | Nimpigie nani dai langu likicheleweshwa au kukataliwa? | Provider contact / IRA complaints
Q16 | Waiting | Is there a waiting period before I can claim? | Je, kuna muda wa kusubiri kabla ya kudai? | Waiting period in wording
Q17 | Family | Can I cover my spouse and children? | Naweza kuwajumuisha mke/mume na watoto? | Family option
Q18 | Group | Can my market association or chama join together? | Je, chama chetu cha soko kinaweza kujiunga pamoja? | Group scheme terms
Q19 | Buying | How do I buy and who do I contact? | Ninanunua vipi na nawasiliana na nani? | Provider contact
Q20 | Comparison | Which is better for me: Jubilee, Britam or CIC? | Ipi ni bora kwangu: Jubilee, Britam au CIC? | Comparison of verified products only
Q21 | Trust | Is my phone number and information safe? | Je, namba yangu ya simu na taarifa zangu ziko salama? | Data protection / consent notice

## Loss_Scenarios
How losses map to product types (hypotheses – validate with traders and insurers)
'Candidate products' refers to Product_Records IDs. Coverage status must be confirmed from policy wording before use in the chatbot.
Risk | Example loss for a mitumba trader | Impact on trader | Product type that could respond | Candidate products (IDs) | Coverage status | What to confirm
Illness / hospitalisation | Trader is admitted and cannot sell; family still needs daily income | Lost daily income plus medical costs | Hospital cash; medical cover | P01, P02, P06 | Likely (needs verification) | Daily benefit amount, waiting period, minimum nights
Accident / injury | Injury on the way to market or while handling bales | Medical bills, weeks without sales | Personal accident | P03, P05 | Likely (needs verification) | Whether traders qualify; benefit limits
Death of the trader | Business stops; family faces funeral costs | Funeral expenses; loss of household income | Funeral / last-expense; life cover | P01, P03, P06 | Likely (needs verification) | Sum insured; who is paid; payout time
Stock lost to fire | Market fire destroys bales and stall | Total loss of working capital | Commercial/MSME property cover | P04 | UNCLEAR – no confirmed product | Does CIC Impact MSME cover include stock and fire? Sum insured; premium
Theft | Stock stolen from stall or storage | Loss of capital | Commercial/MSME property cover | P04 | UNCLEAR – no confirmed product | Theft cover, conditions, security requirements
Eviction / demolition / market closure | Stalls cleared; stock damaged or lost | Loss of site and stock | Likely not insurable under micro products | None | Probable GAP | Ask insurers; say so honestly in the chatbot
Flooding / rain damage | Stock soaked at open-air stalls | Spoiled stock | Commercial/MSME property cover | P04 | UNCLEAR | Weather/flood inclusion
Slow sales / price shocks | Bale prices rise or sales fall | Reduced income | Not insurance – savings or credit | None | GAP (not insurable) | Chatbot should explain this is not covered by insurance
Dependants' health | Child or spouse falls ill | Medical costs, time off work | Family hospital cash / medical | P01, P06 | Possible – family option exists in P01 (2018 info) | Family premium and who counts as dependants

## Affordability
Affordability calculator
Change blue cells. Black cells are formulas. Premiums below are UNVERIFIED headline figures from news.
Trader weekly budget for insurance (KES) | 150 | Assumption: example value only. Ask traders what they can afford (user input, not a published figure).
Product ID | Product | Premium (KES) | Frequency | Weekly equivalent (KES) | Monthly equivalent (KES) | Annual equivalent (KES) | % of weekly budget | Within budget? | Note
P02 | Britam Bima ya Wafanyikazi | 336 | Monthly | 77.5385 | 336 | 4032 | 51.69% | Yes | Headline figure from news; minimum, check actual premium
P04 | CIC Impact portfolio (starting premium, upper bound) | 3000 | Annual | 57.6923 | 250 | 3000 | 38.46% | Yes | 'Below 3,000' per year – upper bound, not an exact premium
P01 | Jubilee Imarisha Jamii (headline) | 20 | Daily | 140 | 606.6667 | 7280 | 93.33% | Yes | Frequency NOT stated in source – 'Daily' is a placeholder assumption; confirm
EXAMPLE | Example product | 100 | Weekly | 100 | 433.3333 | 5200 | 66.67% | Yes | Example row
Assumption: 52 weeks and 12 months per year. Weekly equivalent = daily x 7, monthly x 12 / 52, annual / 52.

## Work_Plan
Work plan: 20–23 Oct 2026
Copy the three sub-tasks into Notion.
Date | Task | Notion sub-task | Owner | Status | Done when
20 Oct | Send outreach email to Jubilee, Britam Connect and CIC Impact; download public documents; start Document_Tracker | 1. Collect official documents | David Guchu | Not started | Emails sent; tracker updated
21 Oct | Phone/visit insurers; fill Product_Records from documents; ask Insurer_Questions | 2. Fill product record sheet and confirm publishing/update frequency | David Guchu | Not started | Each product row has source, date and confidence
22 Oct | Test Trader_Questions with 2–3 traders; refine; review Swahili | 3. Write and group the trader question list | David Guchu | Not started | Questions grouped; gaps noted
23 Oct | Review gaps; mark unverified items; short summary to team | Submit task | David Guchu | Not started | Summary posted in Notion

## Sources
Sources used (all retrieved 20 Oct 2026)
News sources show what exists; they are not authoritative for terms or premiums.
Source | URL | Supports | Type | Reliability for chatbot answers
Capital FM – Jubilee Imarisha Jamii (2018) | https://www.capitalfm.co.ke/business/2018/06/jubilee-insurance-taps-microinsurance-premiums-low-sh20/ | P01 details | News | Low – 2018, verify
Capital FM – Jubilee/FSD Africa insurtech pilots (Oct 2026) | https://capitalfm.africa/jubilee-fsd-africa-partner-with-seven-insurtechs-to-expand-insurance-access/ | P07; November 2026 pilots | News | Medium for context only
Britam – Britam Connect launch (Mar 2025) | https://ke.britam.com/newsroom/britam-connect-to-revolutionize-insurance-for-low-income-households-gig-workers-and-small-businesses | Britam Connect background, 40% market share claim | Insurer press release | Medium (insurer claim)
Business Daily – Britam Bima ya Wafanyikazi | https://www.businessdailyafrica.com/bd/corporate/companies/britam-courts-informal-workers-with-monthly-sh336-medical-cover-5540306 | P02 | News | Low–medium; get brochure
Business Daily – Telkom/Britam Life Bila Noma | https://www.businessdailyafrica.com/bd/corporate/companies/telkom-britam-offer-traders-bundles-insurance-cover-3655304 | P03 | News | Low – older
HapaKenya – CIC Impact launch (30 Jul 2026) | https://hapakenya.com/2026/07/30/cic-insurance-launches-microinsurance-arm-to-safeguard-kenyas-informal-sector/ | P04, P05, P06 | News | Medium for context; get CIC documents
CIC Group press release | https://www.cicinsurancegroup.com/?p=1789 | CIC Impact launch | Insurer press release | Medium
Business Daily – informal sector products | https://www.businessdailyafrica.com/bd/economy/kenyan-insurers-tweak-products-in-race-for-informal-sector-5558574 | List of six licensed micro insurers; irregular income barrier | News | Medium; confirm with IRA list
Insurance Regulatory Authority | https://www.ira.go.ke | Licensed insurers, microinsurance framework | Regulator | High – primary